## Slide 1: General meeting 03.11.2022
Sjur Beyer

## Slide 2: Contents/motivations
Second to last meeting of the semester
This will be a status update

## Slide 3: Progress
~1000 lines of code has been written
Many model runs have been done to test the model
Optuna is implemented
Multiple outputs have been implemented
Automatic model naming schemes and storing configs
Model overfits well to unprocessed seismic data

## Slide 4: Architectures
I think it is reasonable to only focus on TCN
Possible to make reference to publications by Mustafa
LSTM; audio, CNN; image
Seismic === Audio image

## Slide 5: Folder structure
Tree letters denoting group name
Total 26^3 = 17 576 combinations
Models are given a number starting at 0
A model name will then be Groupname / Modelnumber

## Slide 6: Model configs
These are saved in the .json file
These parameters get tweaked by optuna, so I save them to be able to compare what the good performing models have in common
Planning to add ‘feat_aug_dataset’ to have optuna decide what additional data preprocessing is preferable

## Slide 7: Reconstruction

## Slide 8: Not just a kernel size issue (these had ks=8)

## Slide 9: Errors might just be bad regions of loss landscape

## Slide 10: Profiling
Where is the code running | Time per step [ms/step]
NGI Laptop | ~270
Odin w/ # users = ? | ~587
Odin w/ # users = 2 | ~360
Desktop with RTX A2000 | ~35*
* This was running the model with much longer traces and also multiple outputs
This means that I will be able to train 10x as many models, and explore a larger area of the weight space

## Slide 11: Current phase: Data processing
I expect to get started on:
Robust automatic dataset generation
Data preperation
  Normalization, extracting outliers etc
  Correlation of seismic and target:
  Seismic traces and cpt-locations/ai
  -> Cardinality issue
  first value is slightly different

## Slide 12: State of affairs
Cardinality issue, and good dataset management is the only thing thats preventing me from running lots of models.
How to do good correlations?
  GPS data in sgy?
  Also need to do correlation by depth
  What depth is of interest

## Slide 13: Further work
Visualization script still has not been written
  Will incorporate:
    Loss function over time
    Best & worst areas for reconstruction (monochrome w/ red details for error)
    Image of target prediction
    List over what datasets were used
    Summary statistics
    Some model input parameters
  TensorBoard is soon up and running:
  Only needs a little troubleshooting…
  This will allow for me to see how well the training is utilizing the GPU
  May look at using 16bit float for increased computation power
  Huge flatten layers..

## Slide 14: Further work
Geotechnical parameters and evaluating prediction capabilities

## Slide 15: Scope and ambition adjustment
I think I can manage to get feature augmentation done before christmas
In that case I will be having the desktop running optuna all through christmas, and hopefully have some nice model results for January
My last day of the semester will be 19th of December
Last general meeting for the semester will then be on 1.12.2022

## Slide 16: When to start up next semester?